## Vulnerability Register
Finding ID | Vulnerability Title | Affected Asset | Asset Type | Vulnerability Category | Description | Severity | CVSS-Style Score | Exploitability | Business Impact | Exposure | Existing Controls | Recommended Remediation | Compensating Control | Risk Owner | Remediation Owner | Target Date | Status | Validation Status | Residual Risk
VULN-001 | Unsupported third-party library with known security weaknesses | Customer API Service | Application | Vulnerable Component | Simulated application dependency contains known security weaknesses and is beyond the approved maintenance baseline. | High | 8.1 | High | High | Internet-facing | Dependency management; code review; CI/CD controls | Upgrade to a supported library version and validate application compatibility. | Restrict affected functionality where practical and increase monitoring until upgrade. | Head of Engineering | Application Security Lead | 2026-10-30 | Open | Not Yet Validated | High
VULN-002 | Overly permissive cloud storage access policy | Object Storage Bucket | Cloud Storage | Access Control | Simulated storage policy grants broader access than required by least privilege. | High | 8.8 | High | High | Cloud-accessible | IAM; logging; access reviews | Restrict permissions to approved identities and required actions; review bucket access. | Temporary deny policies and enhanced access monitoring. | Cloud Security Owner | Cloud Platform Engineer | 2026-10-23 | Remediation In Progress | Not Yet Validated | High
VULN-003 | Missing security headers on customer-facing web application | Customer Web Portal | Web Application | Security Configuration | Simulated application configuration does not consistently enforce recommended security headers. | Moderate | 6.5 | Medium | Moderate | Internet-facing | WAF; secure development practices | Implement and validate appropriate security headers. | Maintain WAF protections and monitor application traffic. | Head of Engineering | Web Platform Engineer | 2026-11-15 | Open | Not Yet Validated | Moderate
VULN-004 | Excessive privileges assigned to service account | AI Processing Service Account | Identity / IAM | Privilege Management | Simulated service account has permissions beyond those required for normal processing. | High | 8 | Medium | High | Internal / cloud | IAM; access reviews; MFA for human administrators | Reduce permissions to the documented minimum required. | Increase logging and review service-account activity. | Cloud Security Owner | IAM Administrator | 2026-10-23 | Open | Not Yet Validated | High
VULN-005 | Operating system patch level below organizational baseline | Development Virtual Machine | Virtual Machine | Missing Security Patches | Simulated development asset is missing approved security updates. | Moderate | 7.1 | Medium | Moderate | Internal | Endpoint protection; patch management | Apply approved updates and confirm patch baseline compliance. | Restrict network access and increase endpoint monitoring. | IT Operations Manager | Systems Administrator | 2026-11-15 | Remediation In Progress | Not Yet Validated | Moderate
VULN-006 | Database logging configuration does not meet monitoring baseline | Analytics Database | Database | Security Logging | Simulated database configuration does not capture all required security events. | Moderate | 5.9 | Medium | High | Internal / cloud | Cloud monitoring; centralized logging; access controls | Enable required audit events and forward logs to centralized monitoring. | Increase review of available database and cloud logs. | Security Operations Lead | Database Administrator | 2026-11-30 | Open | Not Yet Validated | Moderate
VULN-007 | Publicly reachable administrative endpoint | Management Interface | Web Application | Exposure / Access Control | Simulated administrative interface is reachable from a broader network than required. | Critical | 9.1 | High | Critical | Internet-facing | Authentication; network controls; centralized logging | Remove public exposure and restrict administrative access through approved secure access paths. | Apply emergency network restrictions and heightened monitoring. | Head of Engineering | Cloud Platform Engineer | 2026-10-10 | Remediation In Progress | Not Yet Validated | Critical
VULN-008 | Inadequate secrets rotation interval for application credential | Application Integration Service | Application / IAM | Secrets Management | Simulated application credential has remained active beyond the approved rotation period. | High | 7.5 | Medium | High | Cloud / internal | Secrets management; access controls; monitoring | Rotate the credential and establish automated rotation where feasible. | Restrict credential scope and monitor usage. | Cloud Security Owner | DevOps Engineer | 2026-10-30 | Open | Not Yet Validated | High
VULN-009 | Weak TLS configuration on internal service | Internal Integration Service | Network Service | Cryptographic Configuration | Simulated service permits legacy cryptographic configuration. | Moderate | 6.4 | Medium | Moderate | Internal | Network segmentation; secure configuration standards | Disable legacy protocols and require approved TLS configuration. | Restrict access to trusted network segments. | Security Operations Lead | Network Engineer | 2026-11-30 | Open | Not Yet Validated | Moderate
VULN-010 | Insufficient alerting for repeated authentication failures | Identity Platform | Identity / IAM | Detection & Monitoring | Simulated identity platform lacks appropriately tuned alerting for repeated authentication failures. | Moderate | 6.8 | Medium | High | Cloud / internet-facing | Identity monitoring; centralized logging; MFA | Create and validate detection logic for abnormal authentication failures. | Conduct periodic manual review until automated alerting is validated. | Security Operations Lead | SOC / Detection Engineer | 2026-11-15 | Open | Not Yet Validated | Moderate
VULN-011 | Unused network port exposed on application host | Application Host | Network / VM | Network Configuration | Simulated application host exposes a service port that is not required for business operations. | High | 7.2 | Medium | High | Internet-facing | Network security groups; host firewall; monitoring | Disable unnecessary service and remove corresponding network exposure. | Restrict source networks and monitor connection attempts. | Cloud Security Owner | Systems Administrator | 2026-10-30 | Open | Not Yet Validated | High
VULN-012 | Backup configuration does not meet documented recovery requirement | Application Database Backup | Backup / Cloud | Resilience Configuration | Simulated backup configuration does not consistently meet documented recovery objectives. | High | 7.6 | Medium | High | Cloud / internal | Backup controls; recovery procedures; BCP/DR documentation | Correct backup configuration and conduct recovery validation. | Increase backup verification frequency and document temporary recovery measures. | Technology Operations Manager | Database Administrator | 2026-10-30 | Open | Not Yet Validated | High

## Assessment Summary
Metric | Result
Total Findings | 12
Critical Findings | 1
High Findings | 5
Moderate Findings | 6
Low Findings | 0
Open Findings | 9
Remediation In Progress | 3
Validation Pending | 12

## Methodology
Category | Approach
Severity | Critical, High, Moderate, Low based on simulated technical and business risk.
Prioritization | Technical severity is combined with exploitability, asset criticality, business impact, exposure, existing controls, and threat context.
Critical | Accelerated remediation; immediate or emergency action may be required depending on exposure.
High | Timely remediation, generally targeted within 30 days unless a documented exception is approved.
Moderate | Remediation generally targeted within 60 days.
Low | Remediation generally targeted within 90 days.
Validation | Remediation must be validated before a finding is considered closed.
Risk Acceptance | Unresolved findings require documented justification, risk ownership, approval, and review/expiration date.
Compensating Controls | Temporary controls may reduce exposure while permanent remediation is pending.
Framework Alignment | ISO/IEC 27001:2022, NIST CSF 2.0, NIST SP 800-30, NIST SP 800-53, and CIS Controls.