## Risk-Register
Risk ID | Risk Title | Asset ID | Asset / Process | Risk Description | Threat | Vulnerability / Weakness | Existing Controls | Likelihood | Impact | Inherent Risk Score | Inherent Risk Level | Risk Owner | Treatment Strategy | Treatment Actions | Target Date | Residual Likelihood | Residual Impact | Residual Risk Score | Residual Risk Level
R-001 | Unauthorized Access to Customer & Patient Data | AST-001 | Customer & Patient Data Repository | Unauthorized access to sensitive customer and patient-related information could result in data exposure, privacy violations, regulatory consequences, and loss of customer trust. | Compromised credentials, malicious insider activity, or unauthorized user access | Excessive access privileges, insufficient access reviews, or weaknesses in authentication and authorization controls | Role-based access control; MFA; least-privilege principles; access reviews; identity lifecycle management; security logging | 4 | 5 | 20 | Critical | CISO | Mitigate | Strengthen role-based access controls; perform periodic privileged-access reviews; enforce MFA for all administrative access; monitor anomalous access activity; remove unnecessary permissions | 2026-12-31 | 2 | 5 | 10 | High
R-002 | Unauthorized Modification of Customer & Patient Data | AST-001 | Customer & Patient Data Repository | Unauthorized or improper modification of customer and patient-related data could compromise data integrity, disrupt healthcare workflows, and result in incorrect or unreliable information being used by customers or internal personnel. | Malicious insider activity, compromised privileged account, or unauthorized application activity | Excessive database privileges, inadequate change controls, insufficient monitoring of data modifications, or weak separation of duties | Role-based access control; least privilege; change management; database access restrictions; audit logging; backup and recovery procedures | 3 | 5 | 15 | High | CISO | Mitigate | Restrict privileged database access; implement stronger database activity monitoring; review privileged access regularly; strengthen change approval requirements; validate backup integrity through periodic recovery testing | 2026-12-31 | 2 | 5 | 10 | High
R-003 | Customer Web Application Compromise | AST-002 | Customer Web Application | Exploitation of vulnerabilities in the internet-facing customer application could allow unauthorized access, service disruption, or compromise of sensitive customer information. | External attacker exploiting application vulnerabilities | Unpatched software, insecure application configurations, coding vulnerabilities, or inadequate security testing | Secure development practices; vulnerability management; code review; change management; access controls; security monitoring | 4 | 5 | 20 | Critical | VP Engineering | Mitigate | Strengthen secure SDLC requirements; perform recurring application security testing; prioritize remediation of critical vulnerabilities; implement security-focused code reviews; monitor application activity for indicators of compromise | 2026-12-31 | 2 | 5 | 10 | High
R-004 | API Security / Unauthorized Access | AST-003 | Applicaion Layer | Inadequate API security could allow unauthorized access to application functions or data, resulting in data exposure, service disruption, or abuse of application capabilities. | External attacker exploiting API vulnerabilities or compromised credentials | Weak authentication or authorization controls, insufficient input validation, insecure API configurations, or inadequate API security testing | API authentication and authorization; input validation; access controls; secure development practices; logging and monitoring; vulnerability management | 4 | 5 | 20 | Critical | VP Engineering | Mitigate | Strengthen API authentication and authorization; implement consistent input validation; perform recurring API security testing; review exposed endpoints; monitor API activity for suspicious behavior | 2026-12-31 | 2 | 5 | 10 | High
R-005 | Cloud Misconfiguration | AST-004 | AWS Production Evnironment | Misconfigured cloud infrastructure or security settings could expose systems or data, enable unauthorized access, or disrupt production services. | External attacker exploiting exposed cloud resources or misconfigured services | Insecure security-group rules, excessive permissions, publicly exposed resources, configuration drift, or insufficient cloud security monitoring | IAM; least privilege; security groups; configuration management; vulnerability management; security monitoring; change management | 4 | 5 | 20 | Critical | CTO | Mitigate | Implement continuous cloud configuration monitoring; review security-group rules and IAM permissions; remove unnecessary public exposure; establish configuration baselines; remediate high-risk configuration findings | 2026-12-31 | 2 | 5 | 10 | High
R-006 | Account Compromise / Excessive Privileges | AST-005 | Identity & Access Management | Compromise of user or privileged accounts, combined with excessive permissions, could allow unauthorized access to critical systems and sensitive information. | Credential theft, phishing, credential stuffing, or malicious insider activity | Excessive privileges, weak authentication, stale accounts, inadequate access reviews, or ineffective privileged-access controls | MFA; role-based access control; least privilege; identity lifecycle management; access reviews; security logging | 4 | 5 | 20 | Critical | CISO | Mitigate | Enforce MFA across critical systems; strengthen privileged-access controls; perform periodic access reviews; remove stale accounts and unnecessary permissions; monitor authentication activity for anomalous behavior | 2026-12-31 | 2 | 5 | 10 | High
R-007 | Insufficient Security Monitoring | AST-006 | Security Logging & Monitoring | Inadequate security logging, monitoring, or alerting could delay detection and response to unauthorized activity, increasing the potential impact of security incidents. | Cyber attacker, malicious insider, or unauthorized activity | Incomplete log coverage, insufficient alerting, excessive alert noise, inadequate monitoring of critical systems, or delayed investigation | Centralized logging; security monitoring; alerting; incident response procedures; access controls; log retention | 3 | 4 | 12 | High | CISO | Mitigate | Expand monitoring coverage for critical systems; improve security alerting and correlation; establish monitoring use cases for high-risk events; tune alert thresholds; conduct periodic log-source and detection reviews | 2026-12-31 | 2 | 4 | 8 | Moderate
R-008 | Backup Failure / Recovery Failure | AST-007 | Backup & Recovery Repository | Failure to create, protect, or successfully restore backups could result in permanent or prolonged loss of critical data and extended service disruption following a security incident or system failure. | Ransomware, system failure, data corruption, accidental deletion, or cloud service disruption | Incomplete backup coverage, failed backup jobs, inadequate backup protection, untested recovery procedures, or insufficient recovery monitoring | Automated backups; backup monitoring; access controls; recovery procedures; backup retention; disaster recovery planning | 3 | 5 | 15 | High | COO | Mitigate | Monitor backup jobs and failures; protect backups against unauthorized modification or deletion; perform periodic restoration testing; validate backup coverage for critical systems; document and test recovery procedures | 2026-12-31 | 2 | 5 | 10 | High
R-009 | Endpoint Compromise | AST-008 | Corporate Endpoint Fleet | Compromise of corporate endpoints could provide attackers with unauthorized access to company systems, credentials, sensitive information, or internal resources. | Malware, phishing, ransomware, or malicious software | Unpatched endpoint software, malicious downloads, weak endpoint configuration, inadequate endpoint protection, or user credential compromise | Endpoint security platform; patch management; MFA; device management; security awareness training; access controls | 4 | 4 | 16 | High | COO | Mitigate | Strengthen endpoint protection policies; enforce timely security patching; monitor endpoint security alerts; restrict unauthorized software; improve phishing resistance and security awareness; review endpoint compliance regularly | 2026-12-31 | 2 | 4 | 8 | Moderate
R-010 | Unauthorized Source-Code Access | AST-010 | Source Code Repository | Unauthorized access to source code could expose proprietary intellectual property, introduce malicious changes, or provide attackers with information that could facilitate compromise of production systems. | Compromised developer account, malicious insider, or unauthorized third party | Excessive repository permissions, inadequate access reviews, weak branch protections, or insufficient monitoring of repository activity | Role-based repository access; MFA; branch protection; code review; access reviews; audit logging | 3 | 4 | 12 | High | VP Engineering | Mitigate | Enforce least-privilege repository permissions; strengthen branch protection; conduct periodic access reviews; require MFA; monitor repository activity for suspicious changes or access patterns | 2026-12-31 | 2 | 4 | 8 | Moderate
R-011 | Unauthorized or Malicious Deployment | AST-011 | CI/CD Pipeline | Unauthorized or malicious changes introduced through the CI/CD pipeline could result in compromised production systems, service disruption, or deployment of vulnerable code. | Compromised developer account, malicious insider, or attacker compromising the deployment pipeline | Excessive pipeline permissions, inadequate separation of duties, weak change controls, insecure pipeline configurations, or insufficient deployment validation | Change management; code review; branch protection; access controls; deployment logging; testing requirements | 3 | 5 | 15 | High | VP Engineering | Mitigate | Strengthen CI/CD access controls; enforce separation of duties; require approval for production deployments; protect pipeline credentials and secrets; implement deployment monitoring and audit trails | 2026-12-31 | 2 | 5 | 10 | High
R-012 | Credential / Secret Exposure | AST-012 | Secrets & Credential Store | Exposure or unauthorized disclosure of credentials, API keys, tokens, or other secrets could enable attackers to access applications, cloud infrastructure, or sensitive data. | Credential theft, accidental disclosure, malicious insider activity, or compromised development environment | Hardcoded credentials, excessive access permissions, inadequate secret rotation, accidental disclosure, or insufficient monitoring of secret usage | Centralized secrets management; access controls; least privilege; MFA; credential rotation; security monitoring | 4 | 5 | 20 | Critical | CISO | Mitigate | Enforce centralized secrets management; prohibit hardcoded credentials; strengthen access controls; implement automated secret rotation; monitor secret access; periodically review privileged credentials | 2026-12-31 | 2 | 5 | 10 | High
R-013 | Third-Party Security Risk | AST-15 | Vendor & Third-Party Records | A security weakness or control failure at a third-party provider could expose Northstar systems or data, disrupt critical services, or create compliance and operational risks. | Third-party compromise, supply-chain attack, vendor insider threat, or security control failure | Incomplete vendor due diligence, insufficient security requirements, inadequate ongoing monitoring, or limited visibility into third-party security controls | Vendor security assessments; contractual security requirements; risk classification; access controls; supplier monitoring; incident notification requirements | 3 | 5 | 15 | High | CISO | Mitigate | Strengthen third-party due diligence; classify vendors by risk; require appropriate security and incident-notification provisions; conduct periodic reassessments; track remediation of identified vendor risks | 2026-12-31 | 2 | 5 | 10 | High
R-014 | Delayed Vulnerability Remediation | AST-019 | Vulnerability Management | Delayed identification, prioritization, or remediation of security vulnerabilities could leave critical systems exposed to exploitation and increase the likelihood of a security incident. | External attacker exploiting known vulnerabilities | Incomplete asset coverage, ineffective vulnerability prioritization, remediation delays, or insufficient tracking and escalation | Vulnerability scanning; risk-based prioritization; remediation tracking; patch management; security monitoring; vulnerability reporting | 4 | 4 | 16 | High | CISO | Mitigate | Establish risk-based remediation timelines; prioritize critical and exploitable vulnerabilities; improve asset coverage; track remediation through defined ownership and escalation; report overdue vulnerabilities to leadership | 2026-12-31 | 2 | 4 | 8 | Moderate
R-015 | Customer Information Exposure | AST-020 | Customer Support & Case Management | Unauthorized access to customer support records could expose sensitive customer information, support history, or information submitted during customer interactions. | Unauthorized user, compromised account, malicious insider, or third-party access | Excessive access permissions, inadequate access reviews, weak authentication, insufficient data protection, or improper handling of customer information | Role-based access control; MFA; least privilege; access reviews; security logging; data protection requirements | 3 | 4 | 12 | High | Head of Customer Success | Mitigate | Restrict access to customer records based on business need; conduct periodic access reviews; enforce MFA; strengthen data handling requirements; monitor access to sensitive customer information | 2026-12-31 | 2 | 4 | 8 | Moderate

## Risk-Treatment-Plan
Risk ID | Risk Title | Treatment Strategy | Treatment Actions | Risk Owner | Priority | Target Date | Status | Evidence / Validation | Completion Criteria
R-001 | Unauthorized Access to Customer & Patient Data | Mitigate | Strengthen role-based access controls; perform periodic privileged-access reviews; enforce MFA for all administrative access; monitor anomalous access activity; remove unnecessary permissions | CISO | Critical | 2026-12-31 | Planned | Access review records; MFA configuration evidence; privileged-access reports; security monitoring records | Privileged access is reviewed periodically; MFA is enforced for administrative access; unnecessary permissions are removed; anomalous access monitoring is operational
R-002 | Unauthorized Modification of Customer & Patient Data | Mitigate | Restrict privileged database access; implement stronger database activity monitoring; review privileged access regularly; strengthen change approval requirements; validate backup integrity through periodic recovery testing | CISO | High | 2026-12-31 | In Progress | Database access reviews; database activity monitoring records; approved change records; backup recovery test results | Privileged database access is restricted and reviewed; database activity monitoring is operational; changes require appropriate approval; backup recovery is periodically tested
R-003 | Customer Web Application Compromise | Mitigate | Strengthen secure SDLC requirements; perform recurring application security testing; prioritize remediation of critical vulnerabilities; implement security-focused code reviews; monitor application activity for indicators of compromise | VP Engineering | Critical | 2026-12-31 | In Progress | Application security testing reports; vulnerability remediation records; code review records; secure SDLC documentation; application monitoring alerts | Recurring application security testing is established; critical vulnerabilities are remediated within defined timelines; security-focused code reviews are implemented; application monitoring is operational
R-004 | API Security / Unauthorized Access | Mitigate | Strengthen API authentication and authorization; implement consistent input validation; perform recurring API security testing; review exposed endpoints; monitor API activity for suspicious behavior | VP Engineering | Critical | 2026-12-31 | Planned | API security testing reports; authentication and authorization configurations; endpoint reviews; vulnerability remediation records; API monitoring logs | Critical API vulnerabilities are remediated; authentication and authorization controls are validated; exposed endpoints are reviewed; API security monitoring is operational
R-005 | Cloud Misconfiguration | Mitigate | Implement continuous cloud configuration monitoring; review security-group rules and IAM permissions; remove unnecessary public exposure; establish configuration baselines; remediate high-risk configuration findings | CTO | Critical | 2026-12-31 | In Progress | Cloud configuration assessment reports; IAM and security-group reviews; configuration baseline records; remediation tracking | Critical cloud misconfigurations are remediated; configuration monitoring is operational; IAM and network permissions are reviewed periodically; approved security baselines are established
R-006 | Account Compromise / Excessive Privileges | Mitigate | Enforce MFA across critical systems; strengthen privileged-access controls; perform periodic access reviews; remove stale accounts and unnecessary permissions; monitor authentication activity for anomalous behavior | CISO | Critical | 2026-12-31 | Implemented | MFA configuration records; privileged-access reviews; account lifecycle records; access-remediation records; authentication monitoring logs | MFA is enforced for critical systems; privileged access is reviewed periodically; stale accounts and unnecessary permissions are removed; anomalous authentication monitoring is operational
R-007 | Insufficient Security Monitoring | Mitigate | Expand monitoring coverage for critical systems; improve security alerting and correlation; establish monitoring use cases for high-risk events; tune alert thresholds; conduct periodic log-source and detection reviews | CISO | High | 2026-12-31 | Implemented | Monitoring coverage reports; security detection rules; alert configuration records; log-source reviews; detection testing results | Critical systems have appropriate log coverage; high-risk monitoring use cases are implemented; alerting is tuned; detection coverage is periodically reviewed and tested
R-008 | Backup Failure / Recovery Failure | Mitigate | Monitor backup jobs and failures; protect backups against unauthorized modification or deletion; perform periodic restoration testing; validate backup coverage for critical systems; document and test recovery procedures | COO | High | 2026-12-31 | In Progress | Backup job reports; backup failure alerts; backup access-control reviews; restoration test results; recovery procedure documentation | Backup coverage validated for critical systems; backup failures are monitored and addressed; backups are protected from unauthorized modification or deletion; restoration testing is performed periodically; recovery procedures are documented and tested
R-009 | Endpoint Compromise | Mitigate | Strengthen endpoint protection policies; enforce timely security patching; monitor endpoint security alerts; restrict unauthorized software; improve phishing resistance and security awareness; review endpoint compliance regularly | COO | High | 2026-12-31 | Implemented | Endpoint security configuration records; patch compliance reports; EDR alert records; software-control policies; security awareness records; endpoint compliance reports | Endpoint protection is consistently enforced; critical patches are deployed within defined timelines; unauthorized software is restricted; endpoint alerts are monitored; endpoint compliance is reviewed periodically
R-010 | Unauthorized Source-Code Access | Mitigate | Enforce least-privilege repository permissions; strengthen branch protection; conduct periodic access reviews; require MFA; monitor repository activity for suspicious changes or access patterns | VP Engineering | High | 2026-12-31 | In Progress | Repository access reviews; branch protection settings; MFA configuration records; repository audit logs; access-remediation records | Repository access follows least privilege; branch protection is enforced; MFA is required; access is reviewed periodically; suspicious repository activity is monitored and investigated
R-011 | Unauthorized or Malicious Deployment | Mitigate | Strengthen CI/CD access controls; enforce separation of duties; require approval for production deployments; protect pipeline credentials and secrets; implement deployment monitoring and audit trails | VP Engineering | High | 2026-12-31 | In Progress | CI/CD access reviews; deployment approval records; pipeline configuration; secrets-management records; deployment audit logs | CI/CD access follows least privilege; production deployments require appropriate approval; separation of duties is enforced; pipeline credentials are protected; deployment activity is logged and monitored
R-012 | Credential / Secret Exposure | Mitigate | Enforce centralized secrets management; prohibit hardcoded credentials; strengthen access controls; implement automated secret rotation; monitor secret access; periodically review privileged credentials | CISO | Critical | 2026-12-31 | Planned | Secrets-management configuration; credential-access reviews; secret rotation records; code-scanning results; privileged credential reviews; secret-access logs | Centralized secrets management is enforced; hardcoded credentials are prohibited and monitored; privileged credentials are reviewed periodically; automated rotation is implemented; secret access is logged and monitored
R-013 | Third-Party Security Risk | Mitigate | Strengthen third-party due diligence; classify vendors by risk; require appropriate security and incident-notification provisions; conduct periodic reassessments; track remediation of identified vendor risks | CISO | High | 2026-12-31 | Planned | Vendor security assessments; risk classifications; completed due-diligence records; contractual security requirements; vendor reassessment records; remediation tracking | Vendors are risk-classified; appropriate due diligence is completed; security and incident-notification requirements are documented; high-risk vendors are reassessed periodically; identified vendor risks are tracked through remediation
R-014 | Delayed Vulnerability Remediation | Mitigate | Establish risk-based remediation timelines; prioritize critical and exploitable vulnerabilities; improve asset coverage; track remediation through defined ownership and escalation; report overdue vulnerabilities to leadership | CISO | High | 2026-12-31 | Planned | Vulnerability assessment reports; remediation tracking records; asset coverage reports; remediation SLA records; overdue vulnerability reports | Risk-based remediation timelines are established; critical and exploitable vulnerabilities receive priority; asset coverage is monitored; overdue remediation is escalated; vulnerability status is reported to leadership
R-015 | Customer Information Exposure | Mitigate | Restrict access to customer records based on business need; conduct periodic access reviews; enforce MFA; strengthen data handling requirements; monitor access to sensitive customer information | Head of Customer Success | High | 2026-12-31 | Planned | Customer-data access reviews; MFA configuration records; data-handling procedures; access-monitoring logs; security awareness records | Customer-data access follows business need and least privilege; access is reviewed periodically; MFA is enforced; data-handling requirements are documented; access to sensitive customer information is monitored

## Residual-Risk-Assessment
Risk ID | Risk Title | Inherent Risk Score | Inherent Risk Level | Treatment Strategy | Treatment Status | Residual Likelihood | Residual Impact | Residual Risk Score | Resdidual Risk Level | Risk Owner | Risk Acceptance / Decision | Monitoring Requirements
R-001 | Unauthorized Access to Customer & Patient Data | 20 | Critical | Mitigate | Planned | 2 | 5 | 10 | High | CISO | Residual risk requires continued monitoring and risk-owner oversight | Periodic privileged-access reviews; MFA compliance monitoring; anomalous access monitoring; review of unnecessary permissions
R-002 | Unauthorized Modification of Customer & Patient Data | 15 | High | Mitigate | In Progress | 2 | 5 | 10 | High | CISO | Residual risk requires continued monitoring and risk-owner oversight | Database activity monitoring; privileged-access reviews; change-approval monitoring; backup integrity and recovery testing
R-003 | Customer Web Application Compromise | 20 | Critical | Mitigate | In Progress | 2 | 5 | 10 | High | VP Engineering | Residual risk requires continued treatment, monitoring, and risk-owner oversight | Recurring application security testing; critical vulnerability remediation tracking; secure code reviews; application security monitoring; indicators-of-compromise monitoring
R-004 | API Security / Unauthorized Access | 20 | Critical | Mitigate | Planned | 2 | 5 | 10 | High | VP Engineering | Residual risk requires continued treatment, monitoring, and risk-owner oversight | API security testing; authentication and authorization reviews; exposed-endpoint reviews; vulnerability remediation tracking; API activity monitoring
R-005 | Cloud Misconfiguration | 20 | Critical | Mitigate | In Progress | 2 | 5 | 10 | High | CTO | Residual risk requires continued treatment, monitoring, and risk-owner oversight | Continuous cloud configuration monitoring; IAM and security-group reviews; configuration baseline reviews; public-exposure monitoring; high-risk configuration remediation tracking
R-006 | Account Compromise / Excessive Privileges | 20 | Critical | Mitigate | Implemented | 2 | 5 | 10 | High | CISO | Residual risk is monitored following implementation of identity and access controls | MFA compliance monitoring; privileged-access reviews; stale-account reviews; authentication monitoring; access-remediation tracking
R-007 | Insufficient Security Monitoring | 12 | High | Mitigate | Planned | 2 | 4 | 8 | Moderate | CISO | Residual risk is considered manageable with continued monitoring and improvement of detection coverage | Log-source coverage reviews; detection-rule reviews; alert tuning; high-risk event monitoring; periodic detection testing
R-008 | Backup Failure / Recovery Failure | 15 | High | Mitigate | In Progress | 2 | 5 | 10 | High | COO | Residual risk requires continued treatment, recovery testing, and risk-owner oversight | Backup job monitoring; backup failure tracking; restoration testing; backup access reviews; recovery procedure testing
R-009 | Endpoint Compromise | 16 | High | Mitigate | Implemented | 2 | 4 | 8 | Moderate | COO | Residual risk is considered manageable with continued endpoint monitoring and control maintenance | Endpoint protection alerts; patch compliance monitoring; endpoint security reviews; unauthorized software monitoring; periodic endpoint compliance assessments
R-010 | Unauthorized Source-Code Access | 12 | High | Mitigate | Implemented | 2 | 4 | 8 | Moderate | VP Engineering | Residual risk is considered manageable with continued repository access monitoring and control maintenance | Repository access reviews; branch-protection monitoring; MFA compliance; repository audit logs; periodic review of suspicious access or changes
R-011 | Unauthorized or Malicious Deployment | 15 | High | Mitigate | In Progress | 2 | 5 | 10 | High | VP Engineering | Residual risk requires continued treatment, deployment-control monitoring, and risk-owner oversight | CI/CD access reviews; production deployment approvals; separation-of-duties monitoring; pipeline credential protection; deployment audit logs
R-012 | Credential / Secret Exposure | 20 | Critical | Mitigate | Implemented | 2 | 5 | 10 | High | CISO | Residual risk requires continued monitoring and periodic validation of secrets-management controls | Secret-access monitoring; automated rotation monitoring; privileged credential reviews; code-scanning for exposed secrets; secrets-management configuration reviews
R-013 | Third-Party Security Risk | 15 | High | Mitigate | In Progress | 2 | 5 | 10 | High | CISO | Residual risk requires continued third-party oversight, reassessment, and remediation tracking | Vendor security assessments; risk classification reviews; contractual security requirements; periodic vendor reassessments; vendor remediation tracking
R-014 | Delayed Vulnerability Remediation | 16 | High | Mitigate | In Progress | 2 | 4 | 8 | Moderate | CISO | Residual risk is considered manageable with continued vulnerability remediation and escalation of overdue findings | Vulnerability remediation tracking; critical-vulnerability monitoring; asset coverage reviews; remediation SLA tracking; overdue vulnerability reporting
R-015 | Customer Information Exposure | 12 | High | Mitigate | Planned | 2 | 4 | 8 | Moderate | Head of Customer Success | Residual risk is considered manageable with continued access-control improvements and monitoring | Customer-data access reviews; MFA compliance; data-handling reviews; sensitive-data access monitoring; periodic access-control validation